## Slide 1: Experimental characterization of the deformation and failure fracture behavior of HSS
Student: Feliks Diljak
Advisor: Zinan Li
Supervisor: Junhe Lian
Advanced Manufacturing and Materials
Department of Mechanical Engineering
Aalto University

## Slide 2: Table of Contents
PROJECT OVERVIEW
  Aim and objectives
  Timeline
BACKGROUND and DEVELOPMENT
  Literature review
  Materials
  Experimental plan

## Slide 3: Aim & objectives
Characterize the failure behavior of QP1000 at various temperatures
Characterize the failure behavior of DP1000 at room temperature
Compare the deformation property under each loading condition
Evaluate the difference of the failure performance among QP1000, DP1000 and CP1000 steels

## Slide 4: Timetable
Week 1 Orientation week, initiation of the project
  Aug. 22nd – 26th
Week 2 Lab training, project kick-off
  Postprocessing, testing, DIC setup
Week 3 4 & 5 Experimental tests part A, mid-term review
  DIC measurement on tensile tests
Week 6 7 & 8 Experimental tests part B, progress meeting
  Elevated temperature tensile tests
Week 9 Submission of the final report
  Submission DL: Oct. 21st

## Slide 5: Activities
Project kick-off meeting with Supervisor (Sep. 6th , 11:00 - 12:00)
1st presentation with Professor (early stage)
Weekly meeting with Advisor (Thursdays, 16:00 - 17:00)
Progress meeting
Mid-term presentation (Sep. 23rd, 14:00 - 15:30)
Presentation within the whole group, with a 15-20 minutes presentation and 10 minutes feedback session.
Monitoring meeting – Advisor & Supervisor (Oct. 4th,14:00-15:00)
Feedback after mid-term – Student & Advisor
First draft report (Due by Oct. 9th)
Second/final presentation with all deliverables (Oct. 13th)
Final report (Due by Oct. 21st)
Project report with 20 - 40 pages. Complete results, progress summary, plots, discussion, given template.
Evaluation/feedback of the work – Advisor & Supervisor (Due by Oct. 28)
Review the deliverables & report. Review & finalize the evaluation draft of the student by the advisor.
Internship Project

## Slide 6: Monitoring plan
Daily supervision and weekly discussion with advisior
Scientific discussion in the weekly scientific group meeting
Progressive discussion with supervising Professor once per three weeks
Progressive presentation in group meetings every 1.5 months

## Slide 7: Expected results, deliverables
Testing results and data
  Measured sample dimensions with detailed features
  Photos of the sample before and after tension
  Force-Displacement until fracture
  DIC measurement, images, calculation after postprocessing
Report
  Brief literature review
  Scientific writing
  Progress summary
  Presentation

## Slide 8: Evaluation procedures
To be completed